## RTM
Project Name | OpenCart(Front-end)
Client | OpenCart
Refrence Document | FRS
Created By | Ganga Pandey
Creation Date | 2024-05-31
Approval Date | 2024-06-10
Requirement ID | Requirement Description | Test Scenario ID | Test Scenario Description | Test Case IDs | Test Result | Defect ID | Defect Status
1.1 | Register | TS_001 | Validate the working of Register Account functionality | TC_RF_001 | Pass
|  |  |  | TC_RF_002 | Fail | D1
|  |  |  | TC_RF_003 | Pass
|  |  |  | TC_RF_004 | Pass
|  |  |  | TC_RF_005 | Pass
|  |  |  | TC_RF_006 | Pass
|  |  |  | TC_RF_007 | Pass
|  |  |  | TC_RF_008 | Pass
|  |  |  | TC_RF_009 | Pass
|  |  |  | TC_RF_010 | Pass
|  |  |  | TC_RF_011 | Pass
|  |  |  | TC_RF_012 | Fail | D2
|  |  |  | TC_RF_013 | Pass
|  |  |  | TC_RF_014 | Pass
|  |  |  | TC_RF_015 | Fail | D3
|  |  |  | TC_RF_016 | Pass
|  |  |  | TC_RF_017 | Fail | D4
|  |  |  | TC_RF_018 | Pass
|  |  |  | TC_RF_019 | Pass
|  |  |  | TC_RF_020 | Pass
|  |  |  | TC_RF_021 | Pass
|  |  |  | TC_RF_022 | Pass
|  |  |  | TC_RF_023 | Pass
|  |  |  | TC_RF_024 | Pass
1.2 | Login | TS_002 | Validate the working of Login functionality | TC_LF_001 | Pass
|  |  |  | TC_LF_002 | Pass
|  |  |  | TC_LF_003 | Pass
|  |  |  | TC_LF_004 | Pass
|  |  |  | TC_LF_005 | Pass
|  |  |  | TC_LF_006 | Pass
|  |  |  | TC_LF_007 | Pass
|  |  |  | TC_LF_008 | Pass
|  |  |  | TC_LF_009 | Fail | D5
|  |  |  | TC_LF_010 | Fail | D6
|  |  |  | TC_LF_011 | Blocked
|  |  |  | TC_LF_012 | Fail | D7
|  |  |  | TC_LF_013 | Pass
|  |  |  | TC_LF_014 | Pass
|  |  |  | TC_LF_015 | Fail | D8
|  |  |  | TC_LF_016 | Fail | D9
|  |  |  | TC_LF_017 | Fail | D10
|  |  |  | TC_LF_018 | Fail | D11
|  |  |  | TC_LF_019 | Pass
|  |  |  | TC_LF_020 | Pass
|  |  |  | TC_LF_021 | Pass
|  |  |  | TC_LF_022 | Pass
|  |  |  | TC_LF_023 | Pass
1.3 | Logout | TS_003 | Validate the working of Logout functionality | TC_LG_001 | Pass
|  |  |  | TC_LG_002 | Pass
|  |  |  | TC_LG_003 | Pass
|  |  |  | TC_LG_004 | Pass
|  |  |  | TC_LG_005 | Pass
|  |  |  | TC_LG_006 | Pass
|  |  |  | TC_LG_007 | Fail | D12
|  |  |  | TC_LG_008 | Pass
|  |  |  | TC_LG_009 | Pass
|  |  |  | TC_LG_010 | Pass
|  |  |  | TC_LG_011 | Pass
1.4 | Forgot Password | TS_004 | Validate the working of Forgot Password functionality | TC_FP_001 | Blocked
|  |  |  | TC_FP_002 | Blocked
|  |  |  | TC_FP_003 | Blocked
|  |  |  | TC_FP_004 | Pass
|  |  |  | TC_FP_005 | Blocked
|  |  |  | TC_FP_006 | Blocked
|  |  |  | TC_FP_007 | Blocked
|  |  |  | TC_FP_008 | Blocked
|  |  |  | TC_FP_009 | Blocked
|  |  |  | TC_FP_010 | Blocked
|  |  |  | TC_FP_011 | Blocked
|  |  |  | TC_FP_012 | Blocked
|  |  |  | TC_FP_013 | Blocked
|  |  |  | TC_FP_014 | Blocked
|  |  |  | TC_FP_015 | Pass
|  |  |  | TC_FP_016 | Pass
|  |  |  | TC_FP_017 | Pass
|  |  |  | TC_FP_018 | Pass
|  |  |  | TC_FP_019 | Pass
|  |  |  | TC_FP_020 | Pass
|  |  |  | TC_FP_021 | Pass
|  |  |  | TC_FP_022 | Fail
|  |  |  | TC_FP_023 | Pass | D13
|  |  |  | TC_FP_024 | Blocked
|  |  |  | TC_FP_025 | Blocked
1.5 | Search Product | TS_005 | Validate the working of Search functionality | TC_SF_001 | Pass
|  |  |  | TC_SF_002 | Pass
|  |  |  | TC_SF_003 | Pass
|  |  |  | TC_SF_004 | Pass
|  |  |  | TC_SF_005 | Pass
|  |  |  | TC_SF_006 | Pass
|  |  |  | TC_SF_007 | Pass
|  |  |  | TC_SF_008 | Fail | D14
|  |  |  | TC_SF_009 | Fail | D15
|  |  |  | TC_SF_010 | Fail | D16
|  |  |  | TC_SF_011 | Pass
|  |  |  | TC_SF_012 | Pass
|  |  |  | TC_SF_013 | Fail | D17
|  |  |  | TC_SF_014 | Pass
|  |  |  | TC_SF_015 | Pass
|  |  |  | TC_SF_016 | Pass
|  |  |  | TC_SF_017 | Pass
|  |  |  | TC_SF_018 | Pass
|  |  |  | TC_SF_019 | Fail | D18
|  |  |  | TC_SF_020 | Pass
|  |  |  | TC_SF_021 | Pass
|  |  |  | TC_SF_022 | Pass
1.6 | Product Compare | TS_006 | Validate the working of Product Compare functionality | TC_PC_001 | Blocked
|  |  |  | TC_PC_002 | Blocked
|  |  |  | TC_PC_003 | Blocked
|  |  |  | TC_PC_004 | Blocked
|  |  |  | TC_PC_005 | Blocked
|  |  |  | TC_PC_006 | Blocked
|  |  |  | TC_PC_007 | Blocked
|  |  |  | TC_PC_008 | Blocked
|  |  |  | TC_PC_009 | Blocked
|  |  |  | TC_PC_010 | Blocked
|  |  |  | TC_PC_011 | Blocked
|  |  |  | TC_PC_012 | Blocked
|  |  |  | TC_PC_013 | Blocked
|  |  |  | TC_PC_014 | Blocked
|  |  |  | TC_PC_015 | Blocked
|  |  |  | TC_PC_016 | Blocked
|  |  |  | TC_PC_017 | Blocked
|  |  |  | TC_PC_018 | Blocked
|  |  |  | TC_PC_019 | Blocked
|  |  |  | TC_PC_020 | Blocked
|  |  |  | TC_PC_021 | Blocked
|  |  |  | TC_PC_022 | Blocked
|  |  |  | TC_PC_023 | Blocked
|  |  |  | TC_PC_024 | Blocked
1.7 | Product Display | TS_007 | Validate the working of Display page functionality for the diffrent types of products | TC_PDP_001 | Pass
|  |  |  | TC_PDP_002 | Pass
|  |  |  | TC_PDP_003 | Pass
|  |  |  | TC_PDP_004 | Pass
|  |  |  | TC_PDP_005 | Pass
|  |  |  | TC_PDP_006 | Fail | D19
|  |  |  | TC_PDP_007 | Pass
|  |  |  | TC_PDP_008 | Pass
|  |  |  | TC_PDP_009 | Pass
|  |  |  | TC_PDP_010 | Pass
|  |  |  | TC_PDP_011 | Pass
|  |  |  | TC_PDP_012 | Pass
|  |  |  | TC_PDP_013 | Pass
|  |  |  | TC_PDP_014 | Pass
|  |  |  | TC_PDP_015 | Pass
|  |  |  | TC_PDP_016 | Pass
|  |  |  | TC_PDP_017 | Pass
|  |  |  | TC_PDP_018 | Pass
|  |  |  | TC_PDP_019 | Pass
|  |  |  | TC_PDP_020 | Blocked
|  |  |  | TC_PDP_021 | Pass
|  |  |  | TC_PDP_022 | Pass
|  |  |  | TC_PDP_023 | Pass
|  |  |  | TC_PDP_024 | Pass
|  |  |  | TC_PDP_025 | Pass
|  |  |  | TC_PDP_026 | Pass
|  |  |  | TC_PDP_027 | Pass
|  |  |  | TC_PDP_028 | Pass
|  |  |  | TC_PDP_029 | Pass
|  |  |  | TC_PDP_030 | Pass
|  |  |  | TC_PDP_031 | Pass
|  |  |  | TC_PDP_032 | Pass
|  |  |  | TC_PDP_033 | Pass
|  |  |  | TC_PDP_034 | Pass
|  |  |  | TC_PDP_035 | Pass
|  |  |  | TC_PDP_036 | Pass
|  |  |  | TC_PDP_037 | Pass
1.8 | Add to cart | TS_008 | Validate the working of 'Add to Cart' functionality | TC_ATC_001 | Pass
|  |  |  | TC_ATC_002 | Fail | D20
|  |  |  | TC_ATC_003 | Pass
|  |  |  | TC_ATC_004 | Pass
|  |  |  | TC_ATC_005 | Pass
|  |  |  | TC_ATC_006 | Pass
|  |  |  | TC_ATC_007 | Blocked
|  |  |  | TC_ATC_008 | Pass
|  |  |  | TC_ATC_009 | Pass
1.9 | Home page | TS_011 | Validate the working of Home Page Functionality | TC_HP_001 | Pass
|  |  |  | TC_HP_002 | Pass
|  |  |  | TC_HP_003 | Pass
|  |  |  | TC_HP_004 | Pass
|  |  |  | TC_HP_005 | Pass
|  |  |  | TC_HP_006 | Pass
|  |  |  | TC_HP_007 | Pass
|  |  |  | TC_HP_008 | Pass
|  |  |  | TC_HP_009 | Pass
|  |  |  | TC_HP_010 | Pass
2.1 | Checkout | TS_012 | Validate the working of Checkout functionality | TC_CO_001 | Pass
|  |  |  | TC_CO_002 | Pass
|  |  |  | TC_CO_003 | Pass
|  |  |  | TC_CO_004 | Pass
|  |  |  | TC_CO_005 | Pass
|  |  |  | TC_CO_006 | Pass
|  |  |  | TC_CO_007 | Pass
|  |  |  | TC_CO_008 | Pass
|  |  |  | TC_CO_009 | Pass
|  |  |  | TC_CO_010 | Pass
|  |  |  | TC_CO_011 | Pass
|  |  |  | TC_CO_012 | Pass
|  |  |  | TC_CO_013 | Pass
|  |  |  | TC_CO_014 | Pass
|  |  |  | TC_CO_015 | Pass
|  |  |  | TC_CO_016 | Pass
|  |  |  | TC_CO_017 | Pass
|  |  |  | TC_CO_018 | Pass
|  |  |  | TC_CO_019 | Pass
|  |  |  | TC_CO_020 | Pass
2.2 | My Account | TS_013 | Validate the working of My Account functionality | TC_MA_001 | Pass
|  |  |  | TC_MA_002 | Pass
|  |  |  | TC_MA_003 | Pass
|  |  |  | TC_MA_004 | Pass
|  |  |  | TC_MA_005 | Pass
|  |  |  | TC_MA_006 | Pass
|  |  |  | TC_MA_007 | Pass
|  |  |  | TC_MA_008 | Pass
|  |  |  | TC_MA_009 | Pass
2.3 | Change Password | TS_015 | Validate the working of My Account > 'Change Password functionality | TC_CP_001 | Pass
|  |  |  | TC_CP_002 | Pass
|  |  |  | TC_CP_003 | Pass
|  |  |  | TC_CP_004 | Pass
|  |  |  | TC_CP_005 | Pass
|  |  |  | TC_CP_006 | Pass
|  |  |  | TC_CP_007 | Pass
|  |  |  | TC_CP_008 | Pass
|  |  |  | TC_CP_009 | Pass
|  |  |  | TC_CP_010 | Pass
|  |  |  | TC_CP_011 | Pass
|  |  |  | TC_CP_012 | Pass
|  |  |  | TC_CP_013 | Pass
2.4 | Newsletter | TS_026 | Validate the working of 'Newsletter' functionality | TC_NLT_001 | Pass
|  |  |  | TC_NLT_002 | Pass
|  |  |  | TC_NLT_003 | Pass
|  |  |  | TC_NLT_004 | Pass
|  |  |  | TC_NLT_005 | Pass
|  |  |  | TC_NLT_006 | Pass
|  |  |  | TC_NLT_007 | Pass
|  |  |  | TC_NLT_008 | Pass
|  |  |  | TC_NLT_009 | Pass
|  |  |  | TC_NLT_010 | Pass
|  |  |  | TC_NLT_011 | Pass
|  |  |  | TC_NLT_012 | Pass
|  |  |  | TC_NLT_013 | Pass
2.5 | Contact Us | TS_027 | Validate the working of 'Contact Us' functionality | TC_CU_001 | Pass
|  |  |  | TC_CU_002 | Pass
|  |  |  | TC_CU_003 | Pass
|  |  |  | TC_CU_004 | Pass
|  |  |  | TC_CU_005 | Pass
|  |  |  | TC_CU_006 | Pass
|  |  |  | TC_CU_007 | Pass
|  |  |  | TC_CU_008 | Pass
|  |  |  | TC_CU_009 | Pass
|  |  |  | TC_CU_010 | Pass
|  |  |  | TC_CU_011 | Pass
|  |  |  | TC_CU_012 | Pass
|  |  |  | TC_CU_013 | Pass
2.6 | Different Currencies | TS_031 | Validate the complete Application functionality for different currencies | TC_CR_001 | Pass
|  |  |  | TC_CR_002 | Pass
|  |  |  | TC_CR_003 | Pass

## Summary Report
Project Name: | OpenCart-Frontend | SUMMARY
Application ID/Name: | OpenCart-Frontend | Total Test Cases | 324
Report Date: | 2025-01-30 | Executed | 324
Completed By: | Hafsa Suleman | Pass | 304
|  | Fail | 20
|  | Not Executed | 0
Project Manager: | /
QA Lead: | Hafsa Suleman